## Legend & Notes
International Claiming E2E Test — Legend & Key Improvements
Scenario: Türkiye (TR) ↔ Italy (IT) ¦ Read this first
Status Colour Key
Passed / Closed / Done | Example
Failed / Open | Example
Blocked / In Progress | Example
Not Started | Example
What changed vs. the original file
1. Added an Exit Criteria sheet (was missing) so sign-off has a clear, evidenced gate, not just entry checks.
2. Summary sheet is now a live dashboard: every figure is a formula pulling from E2E Test Execution / Defect Log — no manual re-typing, plus a Pass/Fail chart and a defect-severity chart.
3. E2E Test Execution: added Priority, Currency, Planned Execution Date, Actual Execution Date and Executed By columns for real scheduling and traceability; Execution Result is now a dropdown with automatic colour coding.
4. Entry Criteria: added Owner and Evidence/Comment columns and a Status dropdown so each gate is assigned and verifiable, not just a checkbox.
5. Test Data sheet rebuilt from a single-column field list into an actual repository table (multiple data sets, Environment/Owner/Notes columns) so testers can reuse ready-made data records.
6. Defect Log: added Severity, Priority, Environment, Date Raised, Date Closed and Root Cause columns, all with colour-coded Status.
7. Consistent header banding, alternating row colours, frozen header rows, and AutoFilter on every table for faster scanning and sorting.
8. Colour palette uses a deep blue for headers/titles, with a neutral grey/white body so status colours (green/red/amber) stay the clear signal.

## Summary
International Claiming End-to-End Test — Dashboard
Scenario: Türkiye (TR) ↔ Italy (IT)
Metric | Value | Result | Count
Total Test Cases | 10 | Passed | 4
Passed | 4 | Failed | 0
Failed | 0 | Blocked | 1
Blocked | 1 | Not Started | 5
Not Started | 5
Pass Rate | 40% | Severity | Open Count
Open Critical Defects | 1 | Critical | 1
Open Major Defects | 0 | Major | 0
Open Minor Defects | 0 | Minor | 0
Overall Result | RED

## Entry Criteria
Entry Criteria
Gates to satisfy before test execution starts
ID | Requirement | Owner | Status | Target Date | Evidence / Comment
EC-01 | TR test environment available |  | In Progress
EC-02 | IT test environment available |  | Not Started
EC-03 | Clara interface operational |  | Not Started
EC-04 | Finance systems accessible |  | Not Started
EC-05 | Test users assigned |  | Not Started
EC-06 | Test contract available |  | Not Started

## Exit Criteria
Exit Criteria
Gates to satisfy before test closure / sign-off
ID | Requirement | Owner | Status | Target Date | Evidence / Comment
XC-01 | All planned test cases (TC-01 to TC-10) executed |  | Done
XC-02 | No open Critical or Major defects |  | Not Started
XC-03 | All Minor defects have an agreed workaround or fix date |  | Not Started
XC-04 | Claim, invoice and payment amounts reconcile TR ↔ IT |  | Not Started
XC-05 | Evidence attached for every executed test case |  | Not Started
XC-06 | Sign-off obtained from DTAG management |  | Not Started

## Test Data
Test Data Repository
Reusable data sets for E2E execution — add one row per data set
Data Set ID | Contract Number | VIN | Claim Number | Claim Amount | Invoice Number | Invoice Amount | Currency | Damage Code | Environment | Owner | Notes
DS-01
DS-02
DS-03
DS-04
DS-05
DS-06
DS-07
DS-08

## E2E Test Execution
E2E Test Execution — International Claiming (TR ↔ IT)
Core 10-step contract-to-payment journey
TC ID | Process Step | Description | Source System | Source Tenant | Target System | Target Tenant | Responsible | Priority | Contract Number | VIN | Claim Number | Claim Amount | Currency | Damage Code | Invoice Number | Invoice Amount | Expected Result | Evidence | Execution Result | Planned Date | Actual Date | Executed By | Issues Identified | Ticket Number | Assigned To
TC-01 | Contract Creation | Service contract creation/activation | uiCON/apiCON | TR | iCON Basic | TR | TR Market | High | [8 empty] | Contract successfully activated | Screenshot | Passed
TC-02 | iCON to Clara | Transfer contract to Clara | iCON Basic | TR | Clara | TR | TR Market | High | [8 empty] | Contract visible in Clara | Screenshot/Log | Passed
TC-03 | Claim Creation | Workshop claim created | Clara | IT | Clara | IT | IT Market | High | [8 empty] | Claim successfully created | Screenshot | Passed
TC-04 | Pre-Authorisation | Request sent from IT to TR | Clara | IT | Clara | TR | IT Market | Medium | [8 empty] | Request visible in TR | Screenshot | Passed
TC-05 | Approval | Pre-authorisation approval | Clara | TR | Clara | IT | TR Market | Medium | [8 empty] | Approved in both markets | Screenshot | Blocked
TC-06 | Workshop Reimbursement | Reimbursement executed | Clara | IT | Finance System | IT | IT Market | High | [8 empty] | Payment posting successful | Payment Doc | Not Started
TC-07 | Local Invoice | Invoice creation | Clara | IT | Finance System | IT | IT Market | Medium | [8 empty] | Invoice generated | Invoice PDF | Not Started
TC-08 | International Invoice | Invoice transfer IT to TR | Finance System | IT | Finance System | TR | IT Market | High | [8 empty] | Invoice received successfully | Interface Log | Not Started
TC-09 | International Payment | TR reimburses IT | Finance System | TR | Finance System | IT | TR Market | High | [8 empty] | Payment completed | Payment Ref | Not Started
TC-10 | Clara to iCON | Claim synchronization | Clara | TR | iCON | TR | TR Market | Medium | [8 empty] | Claim visible in iCON | Screenshot | Not Started

## Defect Log
Defect Log
One row per defect raised during E2E execution
TC ID | Ticket Number | Summary | Severity | Priority | Environment | Date Raised | Date Closed | Status | Assigned To | Root Cause
1 | 121 | Defect tedt | Critical | High |  |  |  | Open